Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 12 July 2026 |
| --- | --- |
| Project Name | Customer Registry – MERN Stack Complaint & Customer Management System |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | User Registration | USN-1 | As a customer, I can register with my name, email and password so that I can log complaints. | 2 | High | Karthik |
| Sprint-1 | User Confirmation | USN-2 | As a customer, I can log in with my registered email and password. | 1 | High | Karthik |
| Sprint-1 | Complaint Management | USN-3 | As a customer, I can submit a complaint with my contact details and a description. | 3 | High | Karthik |
| Sprint-1 | Complaint Management | USN-4 | As a customer, I can view the status of each complaint I have raised. | 2 | High | Karthik |
| Sprint-2 | Agent Assignment | USN-5 | As an admin, I can assign a complaint to a support agent. | 3 | High | Karthik |
| Sprint-2 | Agent Workspace | USN-6 | As an agent, I can view only the complaints assigned to me and update their status. | 3 | High | Karthik |
| Sprint-2 | Category Management | USN-7 | As an admin, I can add and list complaint categories. | 2 | Medium | Karthik |
| Sprint-3 | In-app Communication | USN-8 | As a customer or agent, I can send and receive messages tied to a specific complaint. | 3 | Medium | Karthik |
| Sprint-3 | Notifications | USN-9 | As a customer or agent, I receive an in-app notification when something changes on my complaint. | 2 | Medium | Karthik |
| Sprint-4 | Admin Console | USN-10 | As an admin, I can view every complaint, agent and user in the system from one dashboard. | 3 | High | Karthik |
| Sprint-4 | Deployment | USN-11 | As a project owner, I can deploy the client and API so the system is reachable outside localhost. | 2 | Medium | Karthik |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 8 | 6 Days | 01 Feb 2026 | 06 Feb 2026 | 8 | 06 Feb 2026 |
| Sprint-2 | 8 | 6 Days | 07 Feb 2026 | 12 Feb 2026 | 8 | 12 Feb 2026 |
| Sprint-3 | 5 | 6 Days | 13 Feb 2026 | 18 Feb 2026 | 5 | 18 Feb 2026 |
| Sprint-4 | 5 | 6 Days | 19 Feb 2026 | 24 Feb 2026 | 5 | 24 Feb 2026 |

Velocity:

Across the four sprints, the team (a single developer) completed 26 story points in 24 working days, an average velocity of about 6.5 story points per 6-day sprint – consistent, since every planned sprint finished with all its committed points delivered on schedule.

Burndown Chart:

The chart below tracks remaining story points against the ideal linear burndown for Sprint-1 (8 points over 6 working days, shown here on a 10-day axis for clarity of slope).